## Impact Analysis
TPL-026 — Impact Analysis (5 dimension)
Phân tích impact của 1 Change Request — không miss dimension nào.
CR ID: | [ CR-XXX ] |  | Date: | __/__/____
Phân tích bởi: | [ BA + Tech Lead ]
1. 📄 TÀI LIỆU bị ảnh hưởng
Tài liệu | Section | Action | Effort (giờ)
SRS Phân hệ X | 3.2.1, 3.2.5 | Update + thêm flow | 2
UC-001 | Main flow + Alt | Add alt flow | 1
US-005 | Acceptance | Add 2 acceptance | 0.5
Wireframe | Toàn bộ | Redesign 2 màn | 4
Test cases TC-005 | 8 cases | Update 5 + thêm 3 | 2
2. 💻 CODE bị ảnh hưởng
Module | Action | Files | Effort (giờ) | Refactor?
auth-service | Add OTP integration | 5 | 16 | Nhỏ
frontend-login | Add option UI | 3 | 8 | Không
notification-service | Modify support | 2 | 4 | Không
3. 📅 SCHEDULE
Sprint | Impact | Action
Sprint hiện tại | +3 ngày | Pull US-008 ra, add US-005a
Sprint sau | -1 US | Sẽ overload nếu add lại
Go-live deadline | Không ảnh hưởng | Buffer còn 2 tuần
4. 💰 BUDGET
Mục | Cost | Note
Dev hours | 14tr | Fit contingency
QA hours | 2.4tr | Fit contingency
License Zalo OA | 5tr/year | Cost mới
Tổng | 21.4tr | Còn budget contingency: 50tr → OK
5. ⚠ RISK
Rủi ro | Likelihood | Impact | Mitigation
Zalo OA approval mất 2 tuần | High | Medium | Apply ngay (đã apply 13/03)
Zalo API rate limit | Medium | Low | Implement retry + fallback
User confused 2 option | Medium | Low | UX research + A/B test
RECOMMENDATION
Value | ⭐⭐⭐⭐ Cao
Cost | 21.4tr — Reasonable
Effort | 28h dev + 6h QA
Risk | Medium — Có mitigation
Decision recommend | APPROVE